## Sheet1
| PROCESS_ID | PROCESS_DESC | EQUIP_ID | EQUIP_DESC | LINE_ID | MACHINE_ID | TROUBLE_ID | TROUBLE_DESC | TROUBLE_DATE | TROUBLE_STIME | TROUBLE_ETIME | DURATION | ATTEND_BY | CAUSES | ACTION | UPDATED_BY | UPDATED_DATE | UPDATED_TIME | ENGINEER_COMMENT | COMMENT_BY | COMMENT_DATE | COMMENT_TIME
0 | B03 | SPUTTER | E023 | SPT | 205 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/04 | 08:40 | 20:00 | 680 | LIEW YM,REGEN TEAM | - Expansion | -> Clear disk and takeover the machine. -> Take down PQ result and TDU vibration result. -> Fully stop machine and copy all datas needed. -> Vent full system and call out all carriers. -> Stop and purge all cryopumps and stop all turbopumps & drypump. -> Remove All GVs and GV covers. -> Remove all youtec guns, youtec guns and shield parts. -> Remove the URF all data loggers(NI) -> Remove all TDU logger. -> Remove youtec & cap etch gun and blank off chamber. -> Dismantle youtec and cap etch URF cable. -> Remove all gv cylinder & air piping and power cable. -> Install the new GV securing block. -> Change C2 & C3 magnetic shield. -> Handover tmr. C2 Old : 180751K C3 Old : 180754K | 20150023 | 2021/01/04 | 19:58:32
1 | B03 | SPUTTER | E023 | SPT | 205 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/05 | 08:15 | 18:00 | 585 | LIEW YM,REGEN TEAM | - | -> Continues the expansion. -> Swap all the S-cathode chamber,power cable & piping. -> Change C1 and C4 magnetic seal. -> Adjust C1,C2,C3 & C4 transfer pulse. -> Service the GV wall ECV found any scratch.(Check by Engr) | 20150023 | 2021/01/05 | 16:25:02
2 | B03 | SPUTTER | E023 | SPT | 209 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/11 | 09:00 | 20:00 | 660 | LIEW YM,REGEN TEAM | - | -> Take over the machine. -> Fully stop machine and copy all datas needed. -> Vent full system and call out all carriers. -> Stop and purge all cryopumps and stop all turbopumps. -> Remove All GVs and GV covers. -> Remove all youtec guns, youtec guns and shield parts. -> Check and change all faulty bearings. -> Perform kiv activities - Change P9 & P19 10" cryopyump. -> Conversion activity Magnetron P20> Install 2C Magnetron(Remove S Cathode) P21> Install 2C Magnetron(Remove S Cathode) P27> Install VHF(Get from P28) with N2 Etching Ring Magnet P28> Install ICP TS Spacer P7> 15/15mm P10> 12/12mm P13> 5/5mm P16> 10/10mm S Cathode P19> 9/9mm P20> 9/9mm P21> 15/15mm Bias P2> Need P5> Need P7> Need Bias Grounding P11> Need P12> Need P13> Need P24> Need Cap Etching P26> Need Youtec Carbon P27> Need VHF MV Spacer P6> 1mm P7> 0mm P9> 5mm Heater P10> 1mm P11> 4mm S Cathode P12> 3mm S Cathode P13> 3mm P14> 3.5mm S Cathode P15> 3mm P16> 3.5mm S Cathode P17> 8mm P18> 3.5mm P19> 8mm P20> 8mm P24> 6mm Youtec P25> 8mm Heater MFC Install P8 MFC1 with 300sccm Install P10 MFC1 with 300sccm Install P8 MFC4 with 1000sccm(use Lintec MFC) Install P27 MFC 1 300Ar sccm Install P28 MFC 1 300 Ar sccm & MFC 2 300N2 TM Spacer P2> 56/56mm P4> 56/56mm P5> 56/56mm P13> 60/60mm P18> 53/53mm P19> 58/58mm P20> 56/56mm P21> 54/54mm Thin Backing Plates P2> Remove 19mm Type 2 Thin Backing Plate P15 Remove 19mm Type 2 Thin Backing Plate P21> Remove 19mm Type 2 Thin Backing Plate P8> 20mm Ver 2 Thin Backing Plate P11> 20mm Ver 2 Thin Backing Plate P12> 20mm Ver 2 Thin Backing Plate P13> 20mm Ver 2 Thin Backing Plate P15> 20mm Ver 2 Thin backing plate(Get from P20) P19> 20mm Ver 2 Thin Backing Plate P20> normal plate P22> 20mm Ver 2 Thin Backing Plate P23> 20mm Ver 2 Thin Backing Plate GOTS CathodeTS Setting P8> 15mm P11> 9mm P12> 9mm P14> 15mm P16> 9mm P22> 5mm P23> 5mm GOTS CathodeTM Setting P8> 8.2mm P11> 10.2mm P12> 8.2mm P14> 12.7mm P16> 13.7mm P22> 8.2mm P23> 10.2mm UV Lamps P10 Pos1> Need Get fom P3 P14 Pos1> Need Get fom P8 P16 Pos1> Need Get fom P15 P18 Pos1> Need Get fom P17 P22 Pos1> Need Get fom P20 P23 Pos1> Need Get fom P21 Power Controller P3> Remove Pinnacle Plus 5K Controller P4> Remove Pinnacle Plus 5K Controller P5> Remove Pinnacle Plus 5K Controller P10> Install MDX500(Get from P18) P14> DPG-2(2KW) P16> DPG-2(2KW) P18> DPG-2(2KW) P23> MDX500 -Shield Bakes at P7,P11,P12,P13 -> Check all cryopumps' compressors' helium level. P9 cryopump New : 14Z0628C Old : 14Z12067C P19 cryopump New : 14Z06173BS Old : 14Z07120C | 20150023 | 2021/01/11 | 19:23:48
3 | B03 | SPUTTER | E023 | SPT | 209 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/12 | 08:10 | 20:00 | 710 | LIEW YM,REGEN TEAM | - | -> Contious the conversion. -> Service LD & ULD carrier lock. -> RD request P5 bias cylinder shift back to P4. -> Collect S-BAT vibration data - 3 cycles X -> Service all chambers, GVs, GV covers and mv o-rings. -> Check all bias springs' condition contact alignment. -> Start all turbopumps. -> Check all cryopumps' compressors' helium level. -> Install all GVs and GV covers -> Mount all targets, youtec guns and shield parts. -> Check all chambers' rail alignment by using 0.1mm york carrier. -> Check all chambers' shield parts' particles by using UV torch -> Insert 1.5mm carrier to check scratches. -> Insert all new carriers and pump down all chambers. -> Perform internal leak check.OK -> Perform external leak check.NG - Found P14 UV lamp leak,Found P13 bias cylinder not good - Sevice P14 UV lamp & change new bias cylinder for P13 - Leak Check again.-OK -> Autorun and test fire. -> Check all TDU vibration. -> Heat run with toulene air-exhuast for 3600s. -> Monitor alignment. OK -> Handover to nightshift =================================== Regen IC : Liew YM HLL to P3 : Lee TW P4 to P6: Zhang JG P7 to P10 : Roy Wee P11 to P13 : Lum SF P14 to P16 : Vincet Teo P17 to P19: Tham CK P20 to P22 : Thong KS P23 to VTC : Sun XW,Yap YM GV: Jin fei,Tay KH,Low WX LD,ULD & P0 : Koh ZH,Wilson Chan Epson robot : Feng Wei KIV: Wang ZM P24 Cap etching New : ME-03 Old : ME-01 P26 Youtec New : 01 Old : 01 | 20150023 | 2021/01/12 | 18:44:45
4 | B03 | SPUTTER | E023 | SPT | 210 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/13 | 08:05 | 20:00 | 715 | LIEW YM,REGEN TEAM | - | -> Take over from nightshift. -> Remove GVs and GV covers from P3,P4,P9,C2,P10,P23 to P0 -> Remove all youtec guns, youtec guns and shield parts. -> Check and change all faulty bearings. -> Service all chambers, GVs, GV covers and mv o-rings. -> Perform kiv activities - Check P23 TDU any scratches on top, if have need to adjust rail alignment (NGAI) - Change P1 & P10 10" cryopump. - Check P23 to P24 transfer pulse alignment. - Check P19,P24 & P25 cotoon bud.-OK - Check P15 TDU motor connection to see if any wire connector widen.-OK - Change P13 & P14 air vent valve,Change both value - Remove cap etch pos 1 & pos 2 UV lamp,Keep for spare. - Swap all HV cable and junction box.-Done Convesion Magnetron P1> Blank P3> Chg P1 2C to P3(Remove P3 Heater) P4> Install 2A Magnetron P9> Chg P4 2C to P9(Remove P9 Heater) P10> Intstall Heater with 105mm dia reflector(Use Normal PBN Plate), Heater Get from P9 P11> Install S Cathode with 2C Magnetron(S Cathode get from P10) P13> Chg P12 2C to P13 P18> Blank P21> Install S Cathode with 2C Magnetron(S Cathode get from P13) P22> Chg P23 2C to P22 P23> Install S Cathode with 2C Magnetron(S Cathode get from P22) P24> Install Momentive Heater with 105mm dia reflector Plate(Get from P25) P25> Install Cap Etching CVD(Get from P24) Continous Next page | 20150023 | 2021/01/13 | 21:30:35
5 | B03 | SPUTTER | E023 | SPT | 210 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/13 | 20:00 | 23:00 | 180 | LIEW YM,REGEN TEAM | - | -> Continues the conversion TS Spacers P2> 15/15mm P3> 15/15mm P4> 15/15mm P5> 12/12mm P6> 12/12mm P9> 12/12mm P10> 20/20mm Heater P13> 20/20mm P14> 10/10mm P15> 15/15mm S Cathode P17> 15/15mm P19> 10/10mm P21> 5/5mm S Cathode P22> 9/9mm P23> 5/5mm S Cathode P24> 20/20mm Heater P25> 23/23mm Cap Etch MV Spacer P1> 2mm P2> 10mm P3> 11mm P4> 6mm P5> 10mm P6> 8.5mm P7> 9.5mm P8> 0mm P9> 0.8mm P10> 3mm P11> 1.2mm P12> 1.3mm P13> 2mm P14> 1mm P16> 1.8mm P18> 2mm P19> 1mm P20> 2.5mm P22> 2.3mm P23> 9mm P24> 2.5mm GOT S Cathode TS Spacer P11> 3mm P12> 7mm P15> 15mm P21> 20mm P23> 9mm GOT S Cathode TS Spacer P11> 10.7mm P12> 10.2mm P15> 10.2mm P21> 10.2mm P23> 10.2mm MFC Install Argon Charging Tanks at P8 and P9 Install P8 MFC4 with 1K sccm MFC(Get from P7) Install P9 MFC4 with 1K sccm MFC TM Spacer P3> 56/56mm P4> 56/56mm P8> 56/56mm P9> 54/54mm P13> 56/56mm P14> 53/53mm P16> 56/56mm P20> 56/56mm Thin Blacking Plate P9> Ver 2 20mm(Get from P10) P11> Type 2 19mm(Get from P12) P12> Ver 2 20mm(Get from P11) P14> Ver 2 20mm(Remove) P16> Ver 2 20mm(Remove) P20> Ver 2 20mm(Remove) P22> Type 2 19mm(Remove) Bias P6> Need Get from P4 P8> Bias Grounding P25> Need Cap Etch CM Gauge P9> Need 1 Torr Ulvac(Get from P10) P19> Need 1 Torr Ulvac(Get from P18) P20> Need 1 Torr Ulvac(Get from P5) P21> Need 1 Torr Ulvac(Get from P6) P22> Need 1 Torr Ulvac(Get from P7) P23> Need 1 Torr Ulvac(Enable) P25> Need 0.1 Torr Anelva(Get from P24) UV Lamps P2> Pos 1 UV Get from store/Check online still have P3> Pos 1 UV Get from store/Check online still have P5> Pos 1 UV P6> Pos 1 UV P7> Pos 1 UV Get from P4 P9> Pos 1 UV Get from store/Check online still have P11> Pos 1 UV Get from P19 P12> Pos 1 UV Get from P13 P14> Pos 1 UV Get from P15 P16> Pos 1 UV Get from P17 P20> Pos 1 UV Get from P21 P23> Pos 1 UV Get from P22 Shield bake P4 to P9 P5 to P12 P10 to P11 Install shield bake to P13 I>nstall MDX 500 for P13,P15,P17,P23(P13 Get from P19) >Remove DPG-2KW from P13 and P21 >Swap P9 10" pump with P6 10" JKN Enhanced pump(P9 needs 10"JKN Enhanced pump) > Check all cryopumps' compressors' helium level. > Service all chamber and MV P1 Cryopump No New : 14Z10146C Old : 14Z10072C P10 Cryopump No New : 14Z12025C Old : 14Z06261C | 20150023 | 2021/01/13 | 21:48:22
6 | B03 | SPUTTER | E023 | SPT | 210 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/14 | 08:15 | 20:10 | 715 | REGEN TEAM | Full Regen | > Continue Conversion > Service all chambers, GVs, GV covers and mv o-rings. > Perform kiv activities -Collect S-BAT vibration data - 3 cycles X -Toulene canister weight : 10.89 KG -Chg LD vacuum motor -Check LD ULD carrier lock condition, perform greasing -Perform carrier centreing check -Engineer requested to change P24 TDU > Check all bias springs' condition contact alignment. > Start all turbopumps. > Check all cryopumps' compressors' helium level. > Install all removed GVs and GV covers > Mount all targets, youtec guns and shield parts. > Check all chambers' rail alignment by using 0.1mm york carrier. > Check all chambers' shield parts' particles by using UV torch > Insert 1.5mm carrier to check scratches. > Insert all new carriers and pump down all chambers. > Perform internal leak check.NG -P24 gv leak when vent > Perform External leck check . NG -P9 Rear TS spacer leak -P10 Rear TS spacer leak -P4 vent valve leak -Ld bottom cover leak -Ld vac gv face plate leak > Autorun and test fire. > Check all TDU vibration. > Heat run with toulene air-exhuast for 300s > Handover to night shift for monitor alignment ========================================== Regen IC : Tan Sin Choon, Steven Chung HLL to P5 : Low wx, Tay kh (Liew ym) P6 to C2 : Lee tw P10 to P14 : Roy wee P15 to P18 : Lin zg P19 to P23 : Sun xw P24 to VTC : Yap ym, Zhang jg GV : Jin fei KIV : Tan sc, Choong hy, Ong jx Ld, Uld, P0 : Wang zm, Wilson Chan, Koh ch P25 Cap etching New : CE-03 Old : CE-07 P26 youtec New :07 Old : 08 | 20003681 | 2021/01/14 | 19:55:36
7 | B03 | SPUTTER | E023 | SPT | 211 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/22 | 08:30 | 20:10 | 700 | REGEN TEAM | Conversion | -> Take over the machine. > Fully stop machine and copy all datas needed. > Vent full system and call out all carriers. > Stop and purge all cryopumps and stop all turbopumps. > Remove GVs and GV covers.from 23 to P0 > Remove all youtec guns, youtec guns and shield parts. > Check and change all faulty bearings. > Perform kiv activities Install P28 GV Cylinder Block Assembly Chg all chambers ceiling shields > Perform Conversion Magnetron P22> Install S Cathode with 2C Magnetron P23> Install Cap Etch CVD P24> Install ICP with Argon Gas pipe P27> Install ICP with N2 Gas pipe P28> Install ICP with Argon Gas pipe TS Spacer P6> 9/9mm P12> 9/9mm P15> 9/9mm P22> 10/10mm P23> 23/23mm P24> 0mm Bias P1> Need P2> Need P3> Need P6> Bias Grounding(Not activated) P10> Need S Cathode P11> Need S Cathode P14> Need P16> Need P18> Need S Cathode P19> Need P22> Need S Cathode P23> Need Youtec Cap Etch P24> Need ICP with RPG50 P26> Need Youtec Carbon P27> Need ICP with RPG50 P28> Need ICP CM Gauge P4> Need 1 Torr P5> Need 1 Torr P6> Need 1 Torr P7> Need 1 Torr P9> Need 1 Torr P10> Need 1 Torr P11> Need 1 Torr P12> Need 1 Torr P13> Need 1 Torr P14> Need 1 Torr P15> Need 1 Torr P16> Need 1 Torr P17> Need 1 Torr P18> Need 1 Torr P23> Need 0.1 Torr P24> Need 1 Torr P26> Need 0.1 Torr P27> Need 1 Torr P28> Need 1 Torr P0> Need 1 Torr MFC P23> MFC1 100sccm Ar P24> MFC1 200sccm Ar MFC2 300sccm Ar P27> MFC1 200sccm Ar P28> MFC1 200sccm Ar MFC2 300sccm Ar TM Spacer P2> 58/58mm P3> 54/54mm P14> 58/58mm Thin Backing P2> Need Type 2 P4> Need Ver 2 P7> Need Ver 2 P10> Need Ver 2 P11> Need Ver 2 P13> Need Ver 2 P14> Need Ver 2 P15> Need Ver 2 P18> Need Ver 2 P19> Need Ver 2 P20> Need Type 2 P21> Need Ver 2 P22> Need Ver 2 UV Lamps P3 Pos1> Need P4 Pos1> Need P7 Pos 1> Need P14 Pos1> Need P16 Pos1> Need P19 Pos1> Need P20 Pos1> Need LC> Need > Install P24 with 1L TMP with 8" orifice > Check all bias springs' condition contact alignment. > Install all removed GVs and GV covers > Mount all targets, youtec guns and shield parts. > Check all chambers' rail alignment by using 0.1mm york carrier. > Check all chambers' shield parts' particles by using UV torch > Continue next day | 20003681 | 2021/01/22 | 19:27:31
8 | B03 | SPUTTER | E023 | SPT | 211 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/24 | 08:30 | 18:00 | 570 | LIEW YM,LIEW SE,ROY WEE | - | > Continous the conversion. > Install the youtec. > Insert 1.5mm carrier to check scratches. > Insert all new carriers and pump down all chambers. > Change toluene bottle. > Perform internal leak check. OK > Perform External leck check . OK > Perform HV cable check and functional test. > Autorun and test fire. > Heat run with toulene air-exhuast for 3600s P23 Etch New : ME-04 P26 Youtec New :02 | 20150023 | 2021/01/26 | 16:27:56
9 | B03 | SPUTTER | E023 | SPT | 211 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/25 | 08:40 | 12:00 | 200 | LIEW YM,ROY WEE,LIEW SE,KOH CH,WANG ZM,WILSON,YAP YM | - | > Monitor alignment > Check all TDU vibration. > Clear disk. > Collect S-BAT vibration data - 3 cycles X > P7 R1 test fire lower limit.( Bypass NI-logger) OK > Help lay the NI-logger cable. > Heat run. > Handover. | 20150023 | 2021/01/25 | 15:36:37
10 | B03 | SPUTTER | E023 | SPT | 208 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/27 | 08:10 | 20:00 | 710 | LIEW YM,REGEN TEAM | - Conversion | GOT S Cathode TS Setting P11> 5mm P12> 5mm P16> 15mm P21> 9mm P23> 14mm GOT S Cathode TM Setting P11> 10.7mm P12> 10.7mm P16> 10.7mm P21> 10.7mm P23> 10.7mm TM Spacer P1> 56/56mm P3> 56/56mm P9> 54/54mm P13> 56/56mm P14> 56/56mm P15> 56/56mm P19> 56/56mm P20> 56/56mm P22> 56/56mm MFC Install Radial Gas Feedback at P7 Install P7 MFC1 with 200sccm MFC Install P7 MFC2 with 200sccm MFC Install P7 MFC3 with 200sccm MFC Install P7 MFC4 with 200sccm MFC Install P8 MFC1 with 200sccm MFC UV Lamp P1> Need Get from P4 P2> Need P5> Need P6> Need P18> Need(Get from P19) P21> Need P23> Need(Get from P22) Install MDX500 at P14,P23 Install DPG 2K at P16,P18 and P21(Get from P15,P17,P19) Install SHDI Ver 2 Thin Backing Plate(20mm depth) at P11 and P12(Get from P10) Remove P12 SHDS Type 2 Thin Backing Plate(19mm depth) Remove SHDI Ver 2 Thin Backing Plate from P14,P16,20,22 Swap P4 10" pump with P10 8" pump(P10 need 10" pump) Swap P5 10" pump with P16 8" pump(P16 need 10" pump) Check CVD settings for P24 and P26 are set correctly Install shield bakes for P1,P2,P3,P5,P6,P11(Some Get get from P16,P18,P21) Disable P12 Shield Bake Remove P1 and P25 Magnet Catcher(M-shield) P25 cap-etch Old : CE-06 P26 youtec gun Old : 14 | 20150023 | 2021/01/27 | 19:48:08
11 | B03 | SPUTTER | E023 | SPT | 208 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/27 | 08:05 | 20:00 | 715 | LIEW YM,REGEN TEAM | - Conversion | -> Take over from nightshift. -> Remove GVs and GV covers from P3,P4,P9,C2,P10,P23 to P0 -> Remove all youtec guns, youtec guns and shield parts. -> Check and change all faulty bearings. -> Service all chambers, GVs, GV covers and mv o-rings. -> Perform kiv activities Perform Cotton bud check for C1, P1,P19,P22, P23,P25 (NGAI) Swap P11 & P27 TDU motor with P0 & P1 (NGAI) Remove P16,18,20 & 21 Bias cylinder for spare (NGAI) Check all E sensor if greasy, record down those greasy E sensor & clean up (NGAI) Check all RMC coupling, record down & chg if NG (NGAI) Chg P10 S cathode F1 water supply valve (NGAI) Chg P26 vent valve (air vent)-->double both chg,use double filter gasket Chg P1 TDU (cotton bud dirty) Conversion Magnetron P1> Install 2C Magnetron P3> Chg P4 2C to P3 P4> Install Momentive PBN Heater with 105mm dia reflector plate(Get from P3) P9> Chg P21 2C to P9 P10> Install P10 with Movable Convex Heater cum Heater distance at 104mm P11> Install S Cathode with 2C Magnetron(Get from P10) P12> P12 S Cathode - No need to install targets(Blank), only remove 2C Magnetron from S Cathode. P13> Chg P11 2C to P13 P15> Chg P16 2C to P15 P16> Install S Cathode with 2C Magnetron(Get from P15) P21> Install S Cathode with 2C Magnetron(Get from P13) P22> Chg P23 2C to P22 P23> Install S Cathode with 2C Magnetron(Get from P22) P24> Install P24 with Movable Convex Heater cum Heater distance at 105mm(Remove Normal Heater) P25> Install Cap Etching CVD TS Spacers P1> 9/9mm P3> 12/12mm P9> 9/9mm P10> 7/7mm Heater P11> 10/10mm S Cathode P13> 5/5mm P14> 15/15mm P15> 5/5mm P16> 10/10mm S Cathode P17> 9/9mm P18> 9/9mm P21> 5/5mm S Cathode P22> 9/9mm P23> 5/5mm S Cathode P24> 7/7mm Heater P25> 23/23mm Cap Etching CVD Bias P3> Need Get from P2 P7> Need, Bias Grounding P11> Need P12> Blank Chamber(Disable it) P13> Need P15> Need P22> Need P23> Need P24> Need,Bias Gounding P25> Need Cap Etching P26> Need CVD Carbon P27> Need VHF P0> Need CM Gauge P9> Need 1 Torr Ulvac P19> Need 1 Torr Ulvac P20> Need 1 Torr Ulvac P21> Need 1 Torr Ulvac P22> Need 1 Torr Ulvac P23> Need 1 Torr Ulvac P25> Need 0.1 Torr Anelva | 20150023 | 2021/01/27 | 19:47:14
12 | B03 | SPUTTER | E023 | SPT | 208 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/28 | 08:10 | 20:00 | 710 | REGEN TEAM | - | > Continue Conversion > Service all chambers, GVs, GV covers and mv o-rings. > Check all bias springs' condition contact alignment. > Start all turbopumps. > Check all cryopumps' compressors' helium level. -Top up compressors 5,6 and 9 > Install all removed GVs and GV covers > Mount all targets, youtec guns and shield parts. > Check all chambers' rail alignment by using 0.1mm york carrier. > Check all chambers' shield parts' particles by using UV torch > 10mm carrier check > Insert 1.5mm carrier to check scratches. > Perform carrier centreing check > Change toluene bottle > Change and check all chamber MV spacer > Install magnet catche shield at P1 and P24 > Insert all new carriers and pump down all chambers. > Perform External leck check from C3 to C4 only ========================================== Regen IC : Tan Sin Choon, HLL to P5 : Low wx, Tay kh P6 to P10 : Lee tw P11 to P15 : Tham C K P16 to P19 : Wang M Y P20 to P23 : Choong H Y P24 to VTC : Yap ym, Lin R Z GV : Zhang J G / 3 triaineer Ld, Uld, P0 : Koh C H.Wilson Chan,Wang Z M Epson Robot : Chan S L P25 Cap etching New : CE-05 P26 youtec New :16 | 20003772 | 2021/01/28 | 19:50:38
13 | B03 | SPUTTER | E023 | SPT | 208 | - | SM2020 | CONVERSION/PLAN DOWN | 2021/01/29 | 08:10 | 16:15 | 485 | REGEN TEAM | - | > Perform internal leak check -Found P5,P19 and P26 internal leak -Change new gate valve..ok >Perform external leak check -Found P13 rear side dowell pin leak -change TS spacer and o-ring. ok > Perform MFC leak check -Found P7 MFC leak -tighter the MFC joint. ok > Perform HV cable check. ok > Perform functional check. ok > Autorun and test fire. > Check all TDU vibration. > Heat run with toulene air-exhuast for 3600s > Input dummy and monitor alignment > Found load epson robot alignment NG > Fully stop machin > Find tube epson robot alignment.ok > Continue monitor aligment.ok > Zeroing all CM gauge > Hand over | 20003772 | 2021/01/29 | 16:44:22