## Sheet1
| LINE_ID | TROUBLE_DESC | TROUBLE_DATE | TROUBLE_STIME | TROUBLE_ETIME | DURATION | ACTION
0 | 209 | CONVERSION/PLAN DOWN | 2021/03/05 | 08:30 | 20:10 | 700 | > Take over the machine. > Fully stop machine and copy all datas needed. > Vent full system and call out all carriers. > Stop and purge all cryopumps and stop all turbopumps. > Remove all youtec guns, youtec guns and shield parts. > Check and change all faulty bearings. > Perform kiv activities -Need to scrub chamber as RD request, P1, P2, P7, P16, P23 -Chg LD P-Robot arm -Chg P10 TDU > Perform Conversion Magnetron P1> Chg P21 2C to P1 P3> Chg P23 2C to P3 P7> Install S Cathode with 2C Magnetron P8> Install Momentve PBN Heater P9> Chg P8 2C to P9 P11> Install S Cathode with 2C Magnetron P21> Install S Cathode with 2C Magnetron P23> Install S Cathode with 2C Magnetron P27> Install ICP with N2 Gas pipe P28> Install ICP with Argon Gas pipe TS Spacer P1> 9/9mm P3> 9/9mm P7> 10/10mm P8> 20/20mm P9> 10/10mm P11> 10/10mm P12> 9/9mm P15> 9/9mm P17> 9/9mm P21> 10/10mm P23> 10/10mm Bias P1> Need P2> Need P3> Need P6> Need P10> Need P11> Need P12> Need P14> Need P16> Need P20> Need P24> Need P26> Need P28> Need MV Spacer P1> 8mm P2> 8mm P3> 8mm P4> 4mm P6> 0.2mm P7> 1mm P8> 4mm P9> 1.5mm P10> 1.5mm P11> 1.5mm P12> 1.5mm P13> 3mm P14> 2mm P15> 8mm P16> 2mm P17> 8mm P18> 2mm P19> 2mm P20> 2mm P21 8mm P22> 8mm P24> 4mm P25> 10mm P27> 14mm MFC Install P6 with Argon Charging Tank Install P6 MFC4 with 1000sccm Argon MFC Install P7 MFC1 with 200sccm Argon MFC Install P8 MFC1 with 200sccm Argon MFC Install P24 MFC1 with 100sccm Argon MFC Install P27 MFC1 with 300sccm Argon MFC Install P27 MFC2 with 300sccm N2 MFC Install P28 MFC2 wih 200sccm N2 MFC Remove P8 MFC3 10sccm MFC Remove P23 MFC3 200sccm MFC TM Spacer P1> 56/56mm P2> 58/56mm P3> 54/54mm P4> 58/56mm P9> 56/56mm P12> 56/56mm P14> 58/56mm P16> 56/56mm P18> 60/56mm P19> 58/56mm P20> 58/56mm S CathodeTM Spacer P7> 44+5mm P10> 44+5mm P11> 44+5mm P13> 44+5mm P15> 44+5mm P21> 44+5mm P22> 44+5mm P23> 44+5mm UV Lamps P4 Pos1> Need P5 Pos1> Need P7 Pos1> Need P14 Pos1> Need P16 Pos1> Need P20 Pos1> Need P21 Pos1> Need LC> Need Thin Backing Plate P2> Type 2, 19mm Pos 1 only P4> Type 2, 19mm Pos 1 only P14> Type 2, 19mm Pos 1 only P18> Type 2, 19mm Pos 1 only P19> Type 2, 19mm Pos 1 only P20> Type 2, 19mm Pos 1 only P21> Type 2, 19mm P7> Ver 2 P10> Ver 2 P11> Ver 2 P13> Ver 2 P15> Ver 2 P22> Ver 2 P23> Ver 2 Pumps Install P6 10"JKN enhanced pump Install P8 with 8" pump Install P10 with 10" pump > Continue Next day Ld PP Arm New : 0606-13738 Old : 1007CHE11619
1 | 209 | CONVERSION/PLAN DOWN | 2021/03/06 | 08:05 | 20:00 | 715 | > Check all bias springs' condition contact alignment. > Start all turbopumps. > Check all cryopumps' compressors' helium level. > Install GV and GV cover for P3,P4,P8,P9,P23,P24,C4 and P26 > Mount all targets, youtec guns and shield parts. > Do the centering check > Do the 10mm check > Check all chambers' rail alignment by using 0.1mm york carrier. > Check all chambers' shield parts' particles by using UV torch > Insert 1.5mm carrier to check scratches. > Insert all new carriers and pump down all chambers. > Perform internal leak check.NG -Found P3 GV cover leak. -Service o-ring. ok -Found P6 gas 4 MFC leak -Tighter the MFC.ok -Found P12 front side TS spacer leak -Change P12 TS spacer.ok > Perform External leck check . OK > Peform HV cable check > Peform functional check > Engineer check the config > Change P26 MV spacer from 4mm to 6mm > Autorun and test fire. > Check all TDU vibration. > Heat run with toulene air-exhuast for 3600s > Monitor alignment > Handover ================================== Regen IC : Tan Sin Choon, HLL to P4 : Liew S E P5 to P7 : Lum S F P8 to P10 : Zhu X H P11 to P13 : Tham C K P14 to P16 : Ong J X C3 to P19 : Roy Wee P20 to P22 : Chan S L P23 to VTC : Yap Y M,Lin R Z GV : Jin fei Ld, Uld, P0 : Koh ch KIV : Tan C H, Choong hy,Wang Z M P24 Cap etching New : CE-09 P26 Youtec New : 07
2 | 211 | CONVERSION/PLAN DOWN | 2021/03/11 | 06:00 | 08:00 | 120 | - Perform checklist - Perform internal leak check - Call out all carriers - Purge all cryopumps and stop Turbopump - Dismantle all target and vacuum shields - Handover day team continue
3 | 211 | CONVERSION/PLAN DOWN | 2021/03/11 | 08:30 | 20:10 | 700 | > Take over the machine > Remove all youtec guns, youtec guns and shield parts. > Check and change all faulty bearings. > Perform kiv activities -P16 UV lamp change -Chg all shields -Secure all UV lamp power box on top of chamber -Remove P24,P27 and P28 12 unit RMC driver -P27 VHF need check if using ceramic rail -Take photo for FCVD sliding MV full OPEN & Half OPEN > Perform Conversion Magnetron P7> Install 2C Magnetron P8> Install S Cathode with 2C Magnetron P9> Install Momentve PBN Heater P10> Chg P9 2C to P10 P12> Install S Cathode with 2C Magnetron P13> Chg P12 2C to P13 P14> Install S Cathode with 2C Magnetron P15> Chg P14 2C to P15 P16> Install S Cathode with 2C Magnetron P18> Chg P16 2C to P18 P20> Install 2C Magnetron P21> Install 2C Magnetron P23> Install S Cathode with 2C Magnetron P24> Install Cap Etching Unit P27> Install 40 Mhz VHF unit TS Spacer P7> 15/15mm P8> 10/10mm P9> 20/20mm P10> 12/12mm P12> 10/10mm P13> 5/5mm P14> 10/10mm P15> 5/5mm P16> 10/10mm P18> 9/9mm P19> 9/9mm P20> 9/9mm P21> 15/15mm P23> 10/10mm P24> 23/23mm Bias P2> Need P4> Need P7> Bias Grounding P11> Need P12> Need P13> Need P24> Need P26> Need P27> Need MV Spacer P4> 8mm P5> 4mm P6> 1mm P7> 0mm P8> 1mm P9> 5mm P10> 1mm P11> 4mm P12> 3mm P14> 3.5mm P15> 3mm P16> 3.5mm P18> 3.5mm P19> 8mm P23> 8mm P24> 6mm P25> 8mm MFC Install P8 MFC4 with 1000sccm MFC Install P10 to P13 with 200sccm Argon MFC Install P23 MFC1 with 200 sccm Argon MFC Install P24 Argon 200 sccm MFC on MFC1 Install P25 Argon 200 sccm MFC on MFC1 Install P28 N2 300 sccm MFC on MFC2 TM Spacer P2> 56/56mm P3> 56/56mm P4> 56/56mm P7> 56/56mm P10> 56/56mm P13> 60/60mm P15> 58/58mm P18> 54/54mm P20> 56/56mm P21> 54/54mm S CathodeTM Spacer P8 44+5mm P11 44+5mm P12 44+5mm P14 44+5mm P16 44+5mm P22 44+5mm P23 44+5mm UV Lamps P1 Pos1> Need P2 Pos1> Need P3 Pos1> Need P6 Pos1> Need P8 Pos1> Need P9 Pos1> Need P11 Pos1> Need P18 Pos1> Need P20 Pos1> Need P23 Pos1> Need LC> Need Pumps Swap P7 10" JKN pump with P7 10" pump(P7 needs 10" JKN pump) > Continue Next day
4 | 211 | CONVERSION/PLAN DOWN | 2021/03/11 | 20:15 | 08:00 | 705 | >> Takeover dayshift >> Service all chambers >> Up side shield for all chambers >> Mount all targets >> Perform bias alignment for P2, P4, P7, P11, P12, P13,P24 and P26 >> Service MV >> Handover dayshift P1 - P8 : Ming yong P10 - P13 : Sunthra P14 - P16 : Jian feng P17 - P21 : Ah seng P22 - P23 : Jian feng
5 | 211 | CONVERSION/PLAN DOWN | 2021/03/12 | 08:30 | 20:10 | 700 | > Take over machine > Perform KIV -Chg all chamber RMC coupling -Service P24,P27 and P28 orifice,change o-ring and bearing > Perform Uld verticalness check > Perform Ld, Uld alignment check > Perform Ld, Uld Epson robot alignment > P14 TDU driver NG -Change driver X 3. > P14 RMC driver NG > Install controllers and Power supply Install P10 with DPG-2(2KW)Improved Software Install P14 with DPG-2(2KW)Improved Software Install P16 with DPG-2(2KW)Improved Software Install P18 with DPG-2(2KW)Improved Software Remove P22 DP-2(2KW) Install MFX 500 at P23 > Perform Carrier centreing > Perform alignment check for Bias > Install all chambers centre shields > Carrier in and Pump down -C4 cannot pump down -Readjust GV blocks > Continue Next day
6 | 211 | CONVERSION/PLAN DOWN | 2021/03/14 | 08:15 | 16:00 | 465 | -> Continous the Conversion. -> Change the 4 toluene bottle. -> Perform internal leak check.OK -> Perform External leck check . NG - Found P19 front side dowel pin,P6 GV cover, P11 relief valve & P15 front side dowel pin leak - Service the P6 GV cover & P11 relief valve,change P15 and P19 TS spacer and cathode 'o' ring - Pump down & leak check.-OK -> Perform MFC leak check.-OK -> Perform HV & bias cable check.-OK -> Perform functional check.-OK -> Change P1 UV lamp.-OK -> Collect S-BAT vibration data - 3 cycles -> Autorun and test fire. -> Check all TDU vibration. -> Heat run with toulene air-exhuast for 3600s -> Monitor alignment-OK -> Handover to RD