## Sheet1
| LINE_ID | TROUBLE_DESC | TROUBLE_DATE | TROUBLE_STIME | TROUBLE_ETIME | DURATION | ACTION
0 | 209 | CONVERSION/PLAN DOWN | 2021/02/04 | 08:30 | 20:10 | 700 | > Take over the machine. > Fully stop machine and copy all datas needed. > Vent full system and call out all carriers. > Stop and purge all cryopumps and stop all turbopumps. > Remove all youtec guns, youtec guns and shield parts. > Check and change all faulty bearings. > Perform kiv activities -Perform Cotton bud check for P0, P10, P11, P17, P22, P23 -Check all E sensor if greasy, record down those greasy E sensor & clean up -CHg P8 10'' enhance pump -Chg P26 CM card -Turn on URF drypump -Chg P4 double vent valve -Change P0 TDU > Perform Conversion Magnetron P1> Blank P3> Install Momentve PBN Heater with 105mm reflector Plate P8> Chg P1 2C to P8 P9> Install Momentve PBN Heater with 105mm reflector Plate P10> Install S Cathode with 2C Magnetron P11> Chg P10 2C to P11 P13> Install S Cathode with 2C Magnetron P14> Chg P13 2C to P14 P15> Install S Cathode with 2C Magnetron P16> Chg P15 2C to P16 P23> Chg P3 2C to P23 TS Spacers P3> 20/20mm P7> 9/9mm P8> 9/9mm P10> 10/10mm P11> 5/5mm P13> 10/10mm P14> 5/5mm P15> 10/10mm P16> 9/9mm P17> 12/12mm P18> 5/5mm P21> 9/9mm P23> 7/7mm P28> 0mm Bias P2> Need P4> Need P7> Bias Grounding P24> Need P26> Need P27> Need MV Spacers P1> 2mm P2> 7mm P3> 5mm P5> 2mm P6> 2.4mm P8> 0.8mm P9> 4mm P10> 0.5mm P11> 1mm P12> 2.5mm P13> 2mm P14> 2mm P15> 2mm P16> 1mm P17> 2mm P18> 1mm P19> 4mm P20> 10mm P21> 2mm P22> 5mm P24> 10mm P25> 6mm P27> 2mm CM Gauge P5> Need 1 Torr P6> Need 1 Torr P7> Need 1 Torr P8> Need 1 Torr P10> Need 1 Torr P11> Need 1 Torr P12> Need 1 Torr P13> Need 1 Torr P14> Need 1 Torr P15> Need 1 Torr P16> Need 1 Torr P17> Need 1 Torr P18> Need 1 Torr P24> Need 0.1 Torr P26> Need 0.1 Torr P27> Need 1 Torr P28> Need 1 Torr P0> Need 1 Torr TM Spacer P2> 56/56mm P4> 54/54mm P5> 56/56mm P6> 56/56mm P7> 56/56mm P8> 54/54mm P11> 57/57mm P14> 58/58mm P16> 58/58mm P17> 56/56mm P18> 56/56mm P19> 55/55mm P20> 58/58mm P21> 56/56mm P23> 54/54mm MFC Install Argon Charging at P7 Install P7 MFC1 with 1K MFC Install P7 MFC2 with 1000sccm MFC Install P6 MFC1 with 200sccm MFC Install P6 MFC2 with 200sccm MFC Install P8 MFC2 with 200sccm MFC Install P24 MFC2 with 200 sccm MFC Install P25 Heater with 200sccm on MFC2 Install P27 MFC1 with 200Ar MFC Install P27 MFC2 with 300N2 MFC Install P28 MFC1 with 200sccm Ar MFC Install P10 MDX500 to P19 Install DPG 2K at P13,P15,P17 Swap P1 10"pump with P18 8" pump Swap P4 8"E pump with P2 10" pump Swap P6 10 JKN Enhanced pump with P14 10" pump Swap P16 10 JKN Enhanced pump with P22 8"E pump Swap P10 10"pump with P20 8" pump > Continue next day
1 | 209 | CONVERSION/PLAN DOWN | 2021/02/05 | 08:30 | 19:30 | 660 | > Continue Conversion > Service all chambers, GVs, GV covers and mv o-rings. > Check all bias springs' condition contact alignment. > Start all turbopumps. > Check all cryopumps' compressors' helium level > Install all removed GVs and GV covers > Mount all targets, youtec guns and shield parts. > Check all chambers' rail alignment by using 0.1mm york carrier. > Check all chambers' shield parts' particles by using UV torch > 10mm carrier check > Insert 1.5mm carrier to check scratches. > Perform carrier centreing check > Change toluene bottle > Install magnet catche shield at P1 and P25 > Insert all new carriers and pump down all chambers. > Change P26 CM guage ( Due to cannot Zero) > Perform internal leak check. OK > Perform External Leak check. NG -P7 front side dowel pin leak -Ld ATM GV face plate leak > Check HV and Bias cable > Perforn Functional test > Autorun and test fire. > Check all TDU vibration. > Heat run with toulene air-exhuast for 3600s > Monitor alignment > Handover to Production ==================================== Regen IC : Tan Sin Choon, Steven Chung HLL to P3 : Yang mh ( Zhang jg) P4 to P6 : Kong dy ( Zhang jg) P7 to P9 : Sun xw C2 to P12 : Lin rz P13 to P15 : Choong hy P16 to P18 : Liew se P19 to P21 : Lee tw P22 to VTC : Roy wee, Yap ym, Tay kw GV : Jin fei Ld, Uld, Rot : Koh ch, Wilson Chan, Liew ym KIV : Tan sc, Ong jx, Wang zm P24 Cap Etching New : ME-01 Old : ME-01 P26 Youtec New :01 Old : 01
2 | 205 | CONVERSION/PLAN DOWN | 2021/02/12 | 08:30 | 20:10 | 700 | > Take over the machine. > Fully stop machine and copy all datas needed. > Vent full system and call out all carriers. > Stop and purge all cryopumps and stop all turbopumps. > Remove all targets and centre shields > Check and change all faulty bearings. > Perform kiv activities -Chg original P12 cryopump 10 -Load and Unload conversion back to 3.5" 25mils -Install all process with UV lamp(heater no need) -Install double air vent valve for all with single valve -Install Load & Unload wire pick -Install 2nd air vent valve for those new chambers. -Change VTC and Uld TDU unit -Toluene canister weight : 12.44KG > Perform Conversion TM Spacer P19> 55/55mm P23> 54/54mm Pumps Remove P1 10"JKN Enhanced Install P1 with 8" pump Install P18 with 10"pump Swap P2 10" pump with P20 8" pump Swap P6 10 JKN Enhanced pump with P14 10" pump Swap P9 10 JKN Enhanced pump with P22 10" pump > Install UV lamp at P10 and P18 > Install 300sccm Agon at P8 MFC1 > Remove P15 and P17 MDX500s > Continue Next day
3 | 205 | CONVERSION/PLAN DOWN | 2021/02/13 | 08:20 | 20:00 | 700 | > Start all turbopumps. > Do the unload alignment and unload epson robot alignment > Mount all targets, youtec guns and shield parts. > Check all chambers' rail alignment by using 0.1mm york carrier. > Check all chambers' shield parts' particles by using UV torch > Insert 1.5mm carrier to check scratches. > Insert all new carriers and pump down all chambers. > Perform internal leak check.OK > Perform external leak check.NG -Found P13 GV cylinder bellow leak Change New GV cylinder New K-S-S4S-0027 Old K-S-S413-0314 -Found P22,P28 and load GV cylinder seal surface leak -Service P22,P28 and load GV cylinder o-ring.ok > Do the HV cable check > Hand over next day HLL to P5 : Lee T W P6 to C2 : Jin Fei P10 to P13 : Lin Z G P14 to P17 : Tham C K P18 to P21 : Zhu X H P22 to VTC : Zhang J G,Yap Y M LD,ULD & P0 : Wang ZM,Roy Wee P24 New youtec Gun : CE-07 P26 Youtec Gun : 10
4 | 205 | CONVERSION/PLAN DOWN | 2021/02/14 | 08:30 | 19:00 | 630 | > Take over machine > Input dummy disk to minitor alignment.NG -Ld double disk -Ld PP robot Vibrate -Ld PP robot wire pick snap X 3 > Clear disk and re do Ld and uld alignment > Change Ld and Uld Application numbers from 468 to 669 > Check Ld and Uld Speed and parameter setting > Change C2 GV due to internal leak > Perform Functional test > Perform S bat vibration data > Change P23 TM spacer from 54 mm to 56 mm( Last min request from Engineer) > Change P24 Cap Etching MV spacer from 10mm to 6mm (Last min request from Engineer) > Change P27 and P28 MFC 1 From 200sccm to 300sccm (Last min request from Engineer) > Remonitor Ld and Uld alignment.NG -Uld aliignment NG -Adjust Uld pulse. NG -Vent and adjust Uld alignment > Handover to Production P24 Cap Etching New : CE-07 P26 Youtec New : 10
5 | 208 | CONVERSION/PLAN DOWN | 2021/02/18 | 08:30 | 20:10 | 700 | > Take over the machine. > Fully stop machine and copy all datas needed. > Vent full system and call out all carriers. > Stop and purge all cryopumps and stop all turbopumps. > Remove all youtec guns, youtec guns and shield parts. > Check and change all faulty bearings. > Perform kiv activities -Check P1 MV opening -Check all chamber RMC coupling, record & chg those NG ones -Chg P6, 7 & 8 GV cylinder -Perform TDU cotton bud check on P10, 12, 13, 16 & 20 > Perform Conversion Magnetron P1> Blank P3> Install Momentve PBN Heater with 105mm reflector Plate P4> Chg P3 2C to P4 P9> Install Momentve PBN Heater with 105mm reflector Plate P10> Install S Cathode with 2C Magnetron P11> Chg P9 2C to P11 P12> Install 2C Magnetron into S Cathode P13> Install S Cathode with 2C Magnetron P15> Install S Cathode with 2C Magnetron P16> Chg P15 2C to P16 P21> Chg P13 2C to P21 P22> Install S Cathode with 2C Magnetron get from P23 P23> Chg P22 2C to P23 P24> Install Cap Etching CVD with Ceiling Top feed P25> Install Momentve PBN Heater with 105mm reflector Plate TS Spacers P3> 20/20mm P9> 20/20mm P10> 10/10mm P11> 5/5mm P13> 10/10mm P14> 5/5mm P15> 10/10mm P16> 9/9mm P17> 12/12mm P18> 5/5mm P21> 9/9mm P22> 10/10mm P23> 7/7mm P24> 23/23mm P25> 20/20mm Bias P2> Need P4> Need P7> Bias Grounding P24> Need P26> Need P27> Need P0> Disable CM Gauge P5> Need 1 Torr P6> Need 1 Torr P7> Need 1 Torr P8> Need 1 Torr P10> Need 1 Torr P11> Need 1 Torr P12> Need 1 Torr P13> Need 1 Torr P14> Need 1 Torr P15> Need 1 Torr P16> Need 1 Torr P17> Need 1 Torr P18> Need 1 Torr P24> Need 0.1 Torr P26> Need 0.1 Torr P27> Need 1 Torr P28> Need 1 Torr P0> Need 1 Torr TM Spacer P2> 56/56mm P4> 54/54mm P5> 56/56mm P6> 56/56mm P7> 56/56mm P8> 54/54mm P11> 57/57mm P14> 58/58mm P16> 58/58mm P17> 56/56mm P18> 56/56mm P19> 54/54mm P20> 58/58mm P21> 56/56mm P23> 56/56mm MFC Install Argon Charging at P7 Install P7 MFC1 with 1K MFC Install P7 MFC4 with 1K MFC Install P8 MFC1 with 300sccm MFC Install P27 MFC1 with 300Ar MFC Install P27 MFC2 with 300N2 MFC Install P28 MFC1 with 300sccm Ar MFC UV Lamp P4> Install P4 Pos1 P5> Need P6> Need P13> Install P13 Pos1 P15> Install P15 Pos1 P17> Install P17 Pos1 P19> Install P19 Pos1 P21> Need P22> Install P22 Pos1 LC> Need Pumps Swap P4 8"pump with P10 10" pump Swap P5 8"pump with P16 10" pump Swap P6 10"JKN Enhanced pump with P8 10" pump Install P22 with 10" JKN Enhanced > Continue Next Day P6 Pumps New : K-S-S4S-0007 Old : K-S-S413-0150 P7 Pumps New : K-S-S413-0279 Old : K-S-S413-0138 P8 Pumps New : K-S-S413-0074 Old : K-S-S413-0161
6 | 208 | CONVERSION/PLAN DOWN | 2021/02/19 | 08:30 | 20:10 | 700 | > Continue Conversion > Remove GVs and GV covers from P23 to VTC > Check and change all faulty bearings. > Service all chambers, GVs, GV covers and mv o-rings. > Perform kiv activities - Change all chambers RMC Coupling - Perform all chamber carrier pulling force checking > Perform Form factor change for Ld, Uld and Epson Robot > Perform Ld, Uld and Epson alignment adjustment > Check all bias springs' condition contact alignment. > Start all turbopumps. > Check all cryopumps' compressors' helium level. > Install all removed GVs and GV covers > Mount all targets, youtec guns and shield parts. > Change toluene bottle > Check all chambers' rail alignment by using 0.1mm york carrier. > Check all chambers' shield parts' particles by using UV torch > Insert 1.5mm carrier to check scratches. > Insert all new carriers and pump down all chambers. > Perform External leck check . > Heat run with toulene air-exhuast for 3600s > Continue next day =================================================== Regen IC : Tan Sin Choon, Steven Chung HLL to P4 : Yang mh (Tham ck) P5 to P9 : Kong dy (Tham ck) C2 to P13 : Chan sl P14 to P17 : Lin zg P18 to P22 : Ji Bing P23 to VTC : Yap ym, Lin rz GV : Jin Fei Ld, Uld, P0 : Wilson Chan, Wang zm Epson Robot : Liew ym KIV : Tan sc, Choong hy P24 Cap Etching New : CE-06 Old : CE-06 P26 Youtec New : 07 Old : 14
7 | 208 | CONVERSION/PLAN DOWN | 2021/02/20 | 08:30 | 17:00 | 510 | > Continue Conversion > Continue perform External leak check. NG -P7 chamber gas inlet joint leak -P6 TC guage piping leak -P10 GV cover block leak -P25 TS Spacer (Front and Rear ) leak -P25 and C4 GV cover leak -P26 vent valve joint leak -Uld ATM faceplate leak -Ld Vac GV bellow lwak > Perform Internal leak check. NG -P16 and P27 leak > Perform HV and Bias cable check > Perform functional test > Autorun and test fire. > Check all TDU vibration. > Heat run with toulene air-exhuast for 3600s > Monitor alignment > Handover to Production
8 | 210 | CONVERSION/PLAN DOWN | 2021/02/24 | 08:10 | 20:00 | 710 | > Take over the machine. > Fully stop machine and copy all datas needed. > Vent full system and call out all carriers. > Stop and purge all cryopumps and stop all turbopumps. > Remove P22 to P0 GVs and GV covers > Remove all youtec guns, youtec guns and shield parts. > Service all chambers, GVs, GV covers and mv o-rings. > Perform kiv activities - Juction box and all bias HV cable.-Done - Chg P26 double vent valve (NGAI) - Chg all chamber RMC coupling (NGAI) - Chg P27 Bias cylinder & matching box - Chg CTC E-sensor - Reset Conveyor power supply before heat run. Magnetron P3> Install Momentve PBN Heater with 105mm reflector Plate(Get from P4) P4> Chg P3 2C to P4 P9> Install Momentve PBN Heater with 105mm reflector Plate P10> Install S Cathode with 2C Magnetron(Get from P11) P11> Chg P9 2C to P11 P13> Install S Cathode with 2C Magnetron(Get from P21) P18> Chg P13 2C to P18 P21> Install 2C Magnetron P22> Install S Cathode with 2C Magnetron get from P23 P23> Chg P22 2C to P23 P24> Install Cap Etching CVD(Get from P25) with Ceiling Top feed P25> Install Momentve PBN Heater with 105mm reflector Plate(Get from P24) TS Spacer P2> 9/9mm P3> 20/20mm Heater P4> 9/9mm P5> 9/9mm P6> 9/9mm P9> 20/20mm Heater P10> 10/10mm S Cathode P13> 10/10mm S Cathode P14> 5/5mm P15> 10/10mm S Cathode P17> 12/12mm P18> 5/5mm P19> 9/9mm P21> 9/9mm P22> 10/10mm P23> 7/7mm P24> 23/23mm Cap Etch P25> 20/20mm Heater Bias P2> Need P4> Need P7> Bias Grounding P24> Need Cap Etch P26> Need CVD Carbon P27> Need VHF CM Gauge P5> Need 1 Torr Ulvac Get from P21 P6> Need 1 Torr Ulvac Get from P22 P7> Need 1 Torr Ulvac Get from P23 P8> Need 1 Torr Anelva P10> Need 1 Torr Ulvac Get from P9 P11> Need 1 Torr Anelva P12> Need 1 Torr Anelva P13> Need 1 Torr Anelva P14> Need 1 Torr Ulvac P15> Need 1 Torr Anelva P16> Need 1 Torr Ulvac P17> Need 1 Torr Anelva P18> Need 1 Torr Ulvac Get from P19 P24> Need 0.1 Torr Anelva Get from P25 P26> Need 0.1 Torr Anelva P27> Need 1 Torr Ulvac P28> Need 1 Torr Ulvac P0> Need 1 Torr Ulvac GOT S Cathode TS Setting P10> 5mm P12> 5mm P13> 15mm P15> 9mm P22> 8mm GOT S Cathode TM Setting P10> 7.7mm P12> 7.7mm P13> 12.7mm P15> 10.7mm P22> 7.2mm TM Spacer P2> 56/56mm P4> 54/54mm P5> 56/56mm P6> 56/56mm P7> 56/56mm P8> 54/54mm P11> 57/57mm P14> 58/58mm P16> 58/58mm P17> 56/56mm P18> 56/56mm P19> 55/55mm P20> 58/58mm P21> 56/56mm P23> 56/56mm
9 | 210 | CONVERSION/PLAN DOWN | 2021/02/24 | 08:15 | 20:00 | 705 | >>Continue page MFC Install Argon Charging at P7(Remove P8 and P9 Argon Charging Tank) Install P7 MFC1 with 1K MFC Install P7 MFC4 with 1K MFC Install P8 MFC1 with 300sccm MFC Install P8 MFC2 with 200sccm MFC Install P9 MFC2 with 200sccm MFC Install P25 MFC1 with 200sccm MFC Install P25 MFC2 with 200sccm MFC Disable/Remove unused MFCs UV Lamp P4> Install P4 Pos1 with UV lamp(Get from P2) P5> Need P6> Need P13> Install P13 Pos1 with UV lamp(Get from P12) P15> Install P15 Pos1 with UV lamp(Get from P14) P17> Install P17 Pos1 with UV lamp(Get from P16) P19> Install P19 Pos1 with UV lamp(Get from P11) P21> Install P21 Pos1 with UV lamp(Get from P20) P22> Install P22 Pos1 with UV lamp(Get from P23) LC> Need Thin Backing Plate (Ver 2, 20mm) P10> Need Get from P9 P11> Need Remove 19mm Type 2 and Insall 20mm Ver2(Get from store) P12> Need P14> Need Get from store P16> Need Get from strore P20> Need Get from strore P22> Need Get from strore Remove P13,P15 and P23 Ver 2 Thin Backing Plates Other Check and Install MDX500 at P17,P19,P23(Remove MDX at P13 ) Install DPG 2K with improved software at P13(Get from from store), P15(Get from store) Check CVD settings for P24 and P26 are set correctly Install shield bakes for P4,P5,P6,P7,P8,P10 Swap P1 10"pump with P18 8" pump(P18 need 10" pump) Swap P9 10 JKN Enhanced pump with P14 10" pump(P14 needs 10 JKN Enchanced pump) Swap P23 10 JKN Enhanced pump with P22 10" pump(P22 needs 10 JKN Enchanced pump) Install Ph 1 Type 2L TMP with 10" orifice at P27 and P28 chambers > continue next day
10 | 210 | CONVERSION/PLAN DOWN | 2021/02/24 | 20:30 | 22:00 | 90 | - Takeover from regen team - Check and top up helium for compressor - Change MV spacers P2 > 7mm P3 > 5mm P4 > 8mm P5 > 2mm P6 > 2mm P7 > 0mm P8 > 0.8mm P9 > 4mm P10 > 0.5mm P12 > 1mm P15 > 2mm P16 > 1mm P18 > 1mm P19 > 4mm P20 > 10mm P21 > 3mm P22 > 5mm P23 > 8mm P24 > 6mm ULC> 6mm P0 > 6mm LC > 6mm - Handover to regen team
11 | 210 | CONVERSION/PLAN DOWN | 2021/02/25 | 08:30 | 19:30 | 660 | > Continue Conversion > Check and change all faulty bearings. > Service all chambers, GVs, GV covers and mv o-rings. > Check Epson Ld and Uld Robot alignment > Check all bias springs' condition contact alignment. > Start all turbopumps. > Check all cryopumps' compressors' helium level. > Install all removed GVs and GV covers > Mount all targets, youtec guns and shield parts. > Change toluene bottle > Check all chambers' rail alignment by using 0.1mm york carrier. > Check all chambers' shield parts' particles by using UV torch > Insert 1.5mm carrier to check scratches. > Insert all new carriers and pump down all chambers. > Change all chamber RMC coupling > Remove 1 set S-Cathode power box > Perform Internal leak check. OK > Perform External leak check .NG -P6 Rear side dowel pin leak -P26 R2 toulene bottle quick joint leak > Perform HV and Bias cable check > Perform Functional test > Autorun and test fire. > Check all TDU vibration. > Heat run with toulene air-exhuast for 3600s > Monitor alignment > Handover to Production ======================================= Regen IC : Tan Sin Choon, Steven Chung HLL to P4 : Kong dy (Wang zm) P5 to P9 : Roy wee C2 to P13 : Lin zg P14 to P17 : Liew se P18 to P22 : Chan sl P23 to VTC : Yap ym, Lin rz GV : Jin Fei Ld, Uld, P0 : Koh ch, Tay kh Epson Robot : Chan sl KIV : Tan sc, Choong hy, Tan ch, Liew ym, Koo sx P24 Cap Etching New : CE-04 Old : CE-03 P26 Youtec New : 11 Old : 08
12 | 210 | CONVERSION/PLAN DOWN | 2021/02/25 | 20:30 | 06:00 | 570 | >> Troubleshoot ULD robot hang issue >> Reset PLC.NG >> Change Uld robot speed.NG >> Fully stop machine >> Vent ULC >> Change Uld robot >> Run wiith empty cassette and monitor >> Run for 2 hours with no stoppages >> Attend to L202 abort >> Fully stop machine >> Perform T-zeroing >> Redo ULC PP robot alignment >> Pump down >> Dummy run >> Monitor alignment.OK >> Heat run >> Handover New Uld PP robot : 0306-10243 Old Uld PP robot : 1009CHE10382